## Milestones
Phase | Start | End | Owner | Status | Notes
Discovery | 2026-05-15 | 2026-05-29 | Digital Workplace | Done | Confirmed pilot scope with support and finance ops.
Document approval | 2026-05-30 | 2026-07-03 | Policy team | At risk | Approved set incomplete; this is the highest launch risk.
Indexing dry run | 2026-06-05 | 2026-06-20 | Maya | On track | Validates ingestion of PDF, TXT, CSV, Excel uploads.
Reviewer training | 2026-06-22 | 2026-07-08 | Maya | On track | Reviewers learn how to inspect retrieved vs used sources.
Demo walkthrough | 2026-07-09 | 2026-07-12 | Omar | On track | Captures the same flow used in the README demo checklist.
Pilot launch | 2026-07-15 | 2026-07-15 | Digital Workplace lead | Pending | Go/no-go depends on the policy approval milestone.

## Dependencies
Item | Depends on | Status | Owner
Pilot launch | Document approval | At risk | Policy team
Reviewer training | Indexing dry run | On track | Maya
Demo walkthrough | Reviewer training | On track | Omar
Production rollout decision | Pilot launch | Pending | Digital Workplace lead